## Dashboard
DPPPrep Project Starter Workbook
KPI | Value | Project control | Owner | Status
Total requirements | 4 | Scope agreed |  | Not started
Complete | 2 | Supplier data requested |  | Not started
Verify | 1 | Source register current |  | Not started
Missing | 1 | Handover checked |  | Not started
Completion % | 50% | NDA/confidentiality agreed |  | Not started
Use this workbook
1 | Define the product and regulatory scope in Product Scope.
2 | Map each required data point to a source, owner and status.
3 | Track supplier dependencies and document revisions.
4 | Use the Handover sheet to package the dataset for implementation.

## Product Scope
Product Scope
Field | Entry
Project / client
Product family
Model / SKU
Product category
Manufacturer
EU economic operator
Target legislation / delegated act
Passport scope / applicability
Target go-live date
Notes

## Requirement Matrix
Requirement Matrix
Requirement ID | Product/SKU | Requirement/data point | Applicability basis | Current value | Status | Source document | Source revision/date | Data owner | Supplier input required | Access/audience | Action/gap | Priority | Target date | Notes
REQ-001 | B48-48V | Manufacturer identification | Battery Regulation Annex XIII / applicable passport data | Example Battery Systems GmbH | Complete | EU Declaration of Conformity | Rev 4 / 2026-05-12 | Compliance |  | Public |  | Medium |  | Illustrative example
REQ-002 | B48-48V | Unique product / battery identifier | Article 77 / identifier provisions | B48-EXAMPLE-001 | Complete | ERP master data | 2026-09 export | Product data |  | Public |  | High |  | Illustrative example
REQ-003 | B48-48V | Recycled content evidence | Applicable battery data requirement |  | Verify | Supplier declaration | 2025-11 | Sustainability | Yes | Restricted / as applicable | Confirm current supplier evidence | High |  | Illustrative example
REQ-004 | B48-48V | Carbon-footprint evidence / applicability | Battery Regulation + current Commission guidance |  | Missing |  |  | Sustainability | Yes | As applicable | Confirm applicability and current reporting format before implementation | Critical |  | Illustrative example

## Source Register
Source Register
Source ID | Document / file | Type | Revision / date | Owner | Products / requirements supported | Verification status | Location / reference | Notes
SRC-001 | EU Declaration of Conformity | Declaration | Rev 4 / 2026-05-12 | Compliance | REQ-001 | Current | Controlled document system | Illustrative
SRC-002 | ERP master-data export | Data export | 2026-09 | Product data | REQ-002 | Current | ERP | Illustrative
SRC-003 | Supplier recycled-content declaration | Supplier evidence | 2025-11 | Sustainability | REQ-003 | Verify | Supplier portal | Check current revision

## Supplier Requests
Supplier Requests
Request ID | Supplier | Supplier part no. | Product/component | Requested data point | Requested evidence | Regulation/applicability | Status | Response / result | Document reference | Revision/date | Verification owner | Due date | Notes
SUP-001 | Example Cell Supplier |  | Cell module | Recycled content | Signed declaration / source evidence | Battery passport preparation | Requested |  |  |  | Sustainability |  | Illustrative

## Data Owners
Data Owners
Data domain | Primary owner | Backup owner | System / source | Supplier dependency | Review frequency | Notes
Product identity | Product data |  | ERP / PLM | No | On change
Manufacturer / operator identity | Compliance |  | QMS / legal records | No | Annual / on change
Materials / chemistry | Engineering |  | BOM / supplier declarations | Yes | On change
Carbon footprint | Sustainability |  | LCA / supplier evidence | Yes | As required
Recycled content | Sustainability |  | Supplier evidence | Yes | As required
Performance / durability | Engineering |  | Test reports / technical files | Possibly | On change
Repair / end-of-life | Service / engineering |  | Manuals / dismantling docs | Possibly | On change

## RACI
DPP RACI
Workstream | Project lead | Compliance | Engineering | Product data / IT | Procurement | Supplier | Notes
Confirm product scope | A | R/C | C | C | I | I | R=Responsible, A=Accountable, C=Consulted, I=Informed
Requirement mapping | A | R | C | C | I | I
Source validation | A | R | R | C | C | C
Supplier data requests | A | C | C | I | R | R
Dataset structuring | A | C | C | R | I | I
Implementation handover | A | C | C | R | I | I
Lifecycle update process | A | C | C | R | C | C

## Handover
Implementation Handover Checklist
Handover item | Owner | Status | Evidence / location | Notes
Scope and applicability confirmed |  | Not started
Requirement matrix reviewed |  | Not started
Source register current |  | Not started
Missing/verify items assigned |  | Not started
Supplier dependencies tracked |  | Not started
Access/audience classifications reviewed |  | Not started
Structured dataset exported |  | Not started
Identifiers / registration responsibilities assigned |  | Not started
Hosting / DPP service-provider interface defined |  | Not started
Lifecycle update ownership defined |  | Not started
Open issues documented |  | Not started
Final review / sign-off completed |  | Not started

## EU Sources
Official EU Sources
Source | What it is useful for | URL | Checked
European Commission - Digital Product Passport | Current Commission DPP overview, timeline and resources | https://single-market-economy.ec.europa.eu/single-market/digital-product-passport_en | 2026-09-28
European Commission - DPP Registry | Registry role, enrolment, user guidance and helpdesk | https://single-market-economy.ec.europa.eu/single-market/digital-product-passport/dpp-registry_en | 2026-09-28
European Commission - Resources & documentation | Current Registry user guide and battery guidance versions | https://single-market-economy.ec.europa.eu/single-market/digital-product-passport/resources-documentation_en | 2026-09-28
European Commission - Batteries / DPP | Battery-specific implementation timeline and guidance | https://single-market-economy.ec.europa.eu/single-market/digital-product-passport/batteries_en | 2026-09-28
EUR-Lex - Regulation (EU) 2023/1542 | Battery passport legal basis, Article 77 and Annex XIII | https://eur-lex.europa.eu/eli/reg/2023/1542/oj | 2026-09-28
EUR-Lex - Regulation (EU) 2024/1781 | ESPR and DPP framework | https://eur-lex.europa.eu/eli/reg/2024/1781/oj | 2026-09-28

## Lists
Status | Priority | Yes/No | Control status
Complete | Critical | Yes | Not started
Verify | High | No | In progress
Missing | Medium |  | Complete
Not applicable | Low |  | Not applicable
In progress
Workbook version | V5 / 2026-09-28